Dakota Drilling and Concrete, Inc.                     Mobile

2235 Statham Blvd., Oxnard, CA 93033		           Doug - (818) 823-6260

Ph (805) 483-5900    Fax (805) 483-5959                        Randy - (805) 889-0034

State license No. 477175

DRAFT SOIL NAIL – TECCO NET INSTALLATION PROPOSAL/CONTRACT

Date:	12/16/25	Plans C-576	The attached Terms and Conditions

Estimator:	Erandy Reyes		are part of this proposal.

SUBMITTED TO:		PROJECT:

Slope Remediation Services	Attn:	Dave Salter	Tecco Net and Soil Nail Installation

3564 Sagunto St, Unit 486	Ph.:	310.699.1274	1643 Woods Drive

Santa Ynez, CA 93460	Fax:	N/A	Los Angeles, CA 90069

BASED UPON DRAWINGS AND DOCUMENTS:

Soils Report:	Feffer Geological Consulting File No. 3392- 55 Dated 04/25/25 (Test Pit Only)

Building Plans:	DRS Engineering, Inc. Project No.2025-202 Dated 10/16/25 Sheet SH-1.0 thru SH-3.1 (5 sheets total)

SCOPE OF WORK – TECCO NET INSTALLATION:

Mobilization

One (1) mobilization is included for the installation scope herein.

Footage

PERMANENT SOIL NAIL INSTALLATION

Drill, Install and grout 157 anchors per plans. Estimated drilling footage……………………..……	     1,663 ln ft		Includes testing of soil nails per plan. *NOTE* Includes up to 10% overage on drilling footage. See Note J.

SCALE, CLEAR, GRUB EXISTING HILLSIDE (See Note H)

Trim and remove existing vegetation if and where required. Scale and remove loose dirt/debris as required by project geotechnical inspector. Export of drilling spoils as required.

Includes export of up to……………………………………………………………………………..….	   70 cu yards

INSTALL TECCO NET BARRIER

Provide materials, men and equipment to install the Tecco Net barrier per plans.

Estimated square footage ……………………………………………………………………………..….	  12,055 sq ft
*NOTE* Includes up to 10% overage on Tecco Net square footage. See Note J.

Proposal / Contract Price Based Upon: Non-Prevailing Wages, No Project Labor Agreement

TOTAL TECCO NET INSTALLATION	$ 591,996

ADD PRICES:	Additional Soil Nails  $ 152.00 per additional lineal foot

Additional Netting	$   23.50 per additional square foot

JOB SPECIFIC QUALIFICATIONS:

- When drilling essentially horizontal soil nail shafts, it is difficult to accurately predict the amount of caving that may occur under any conditions. It should be realized, however, that some caving may occur and could require alternative methods to complete the effected shafts. Caving may result in additional charges.

- This proposal is based upon continuous, uninterrupted drilling and installation. This proposal may have to be adjusted based upon how the participating contractors plan to process the work and is also subject to material availability and Dakota Drilling’s availability when the construction is scheduled to begin.

- The above amount is based strictly upon the details shown in the plans. It does not include any requirements that may be shown in the Soils Report or Soils Report Approval Letter which are not detailed in the plans.

- The quantities shown in this proposal are an estimate only based upon the referenced building plans provided for bidding purposes.

- Dakota Drilling requires full access to the slope from both the top and bottom to facilitate any equipment and apparatus that may be required to complete Tecco Net installation.

- The above referenced plans do not appear to be stamped and approved by building and safety. This proposal may be adjusted to reflect any differences between these plans and the final approved plans. Soil nails for this project will not be ordered until a stamped and approved set of plans is provided to Dakota Drilling.

- If necessary, any obstructions along the slope, including but not limited to surficial drainage/utility pipes, sprinkler/irrigation lines, etc. to be removed by others prior to soil nail installation. Dakota Drilling accepts no responsibility for any damage to any existing pipe or drainage systems that are unable to be removed or located by others.

- The above sum includes up to 70 yards of export, including drilling spoils. Any additional export to be performed as an extra and will be billed per Dakota Drilling’s Standard Labor and Equipment Rate Sheet, attached.

- Excludes hydroseeding. Hydroseeding can be quoted upon request.

- This contract includes up to 10% overage on soil nail drilling footage and up to 10% overage on Tecco Net area to be installed. Any additional nails or netting that exceeds 10% more than what is shown on the engineered set of plans that may be required to complete Tecco Net installation will be billed as an extra per the add prices shown on Page 1.

- Dakota Drilling to be provided access to 1645 Woods Drive as a staging area for equipment and material while on site performing Tecco net installation.

General Terms and Conditions – Soil Nails

PAYMENT SCHEDULE:

Phase of Project 	 Amount Invoiced                    	 When Invoiced                 	Amount 	 Invoice Due

- Mobilization	$ 10% of total contract	Contract Execution	$ 55,974	Pre-Mobilization

- Order Materials	$ Materials	Contract Execution	$152,664	Pre-Mobilization

- Progress Billing	$ Amount completed	Monthly	Installed		30 Days

- SPECIFIC EXCLUSIONS – TO BE PROVIDED BY OTHERS. Unless stipulated to the contrary in the “SCOPE” or “QUALIFICATIONS” on the proposal, the following items are not included and must be provided by others:

  - Uninterrupted supply of potable water at city pressure within 200’ of drilling operations.

  - Bins or clean out location for grout or drilling spoils on project site where drilling operations occur.

  - Dumpster for trash generated by Dakota Drilling and Concrete, Inc. (hereinafter “DDC”) operations, or a designated area to stockpile trash on jobsite. Trash export by others.

  - Staging area within immediate vicinity of drilling operations allowing unimpeded access for DDC equipment and materials.

  - Unimpeded access for DDC equipment, apparatus, and personnel in front of, and at, the existing projected soil nail angle to install a full-length prefabricated soil nail in a continuous and uninterrupted manner. Interruptions will be billed as an extra as provided in “Delays by Others” below.

  - Clearing, grubbing, chipping, tree removal, spoils removal, ground water removal, dewatering, site dust control, erosion control, and SWPP establishment or maintenance. There are no remedial provisions for contaminated water or soil.

  - All required field engineering, including survey, layout, offsets, center of hole locations, elevations, depths and monitoring.

  - All scheduling and payment for inspections, permits, and fees, including but not limited to, scheduling deputy soils and concrete inspections, concrete testing and record keeping and/or reports.

  - Welding or fabrications.

  - All “potholing” and accurate location of existing utilities, and protection, removal, or relocation of any existing utilities, either above or below ground, which may interfere with the soil nail installation. Power lines closer than legally permissible to be removed or de-energized by others.

  - Shoring, covering open excavations, bracing, underpinning, supporting or protecting existing structures.

  - Furnishing security guards, storage area, sanitary facilities, traffic control, flagmen, or barricades.

  - Premiums for bonds or liability insurance premiums on condominium projects.

- PRELIMINARY INFORMATION: All 20-day preliminary information must be submitted with the contract, including a property address, full legal description, etc. before any material will be ordered, or any work will commence.

- DAILY REPORTS: Owner (or Owner’s agent/representative) must be available to review and acknowledge the DDC daily “Activity Report” which records the day’s job activity and any noteworthy events which may influence the installation or integrity of the soil nails. If Owner does not dispute the daily report in writing when reviewed, or if Owner is not available within 48 hours to sign the daily report, Owner waives the right to later dispute the information recorded in the daily report.

- DESIGN SPECIFICATIONS: DDC accepts no responsibility for pre-designed soil nail specifications, it being understood that DDC is not an architect, engineer or surveyor and will be relying upon the accuracy of all professional reports, measurements, drawings and specifications.

- DEDUCT: No credit will be given for a reduced number of nails or reduced area of Tecco Net.

- CAVING OF SHAFT WALLS: When drilling soil nail shafts, field conditions may cause excessive caving of the shaft walls which can result in additional costs that will be billed as an extra unless specifically included in the Scope of Work on page one of the contract. These additional costs are for extra grout and/or steel casing:

  - EXTRA GROUT – The volume of grout provided in this contract is one and one-half (150%) the amount required for the shaft dimensions shown on the building plans. If the shaft walls collapse, both the shaft and the voids created by the caving may require more grout than is provided in the contract. The excess grout required to close the shaft and fill the voids is not included in this proposal and will be billed as an extra at the rate of $18.50 per 94 lb. bag of cement plus 15% markup (this includes the labor and equipment to install the grout).

  - STEEL CASING – Unless casing is specifically included in the SCOPE OF WORK on page one of the proposal, when field conditions require steel casing to hold the shaft wall open until the soil nail can be installed and the shaft grouted, the existing lineal footage price will be increased by $24.50 per lineal foot of casing up to 8” (203mm) in diameter plus reimbursement for destroyed drill bits plus 15% markup. For projects requiring larger shaft diameters, the additional cost for casing will be the cost of the steel casing materials, plus $450.00 per hour additional installation and removal costs. A hollow stem auger is steel casing with flights welded to the outside, and when required will be billed as using steel casing. The use of casing will be noted in the Daily Report, and these additional costs will be an increase in the contract price without the requirement of a change or extra work order and will be billed as additional drilling costs.

- WAGE RATES & OVERTIME: Unless indicated to the contrary in the Scope portion, this proposal is based upon NON-PREVAILING WAGES, and performing our work in one continuous and uninterrupted manner during normal business hours (8 hrs. per day-Mon thru Fri) with only one move on and off the site (unless additional move-ins are provided for in SCOPE OF WORK on the proposal). If overtime is requested, the overtime hourly wage in excess of straight time, plus payroll burden, will be charged as extra work.

- MATERIALS: The materials used for soil nail installations are custom made for each individual job and cannot be returned to the manufacturer. In addition, cement grout bags are subject to punctures, moisture absorption, etc., and the manufacturers will not accept returns.

- DELAYS BY OTHERS: If progress of our work is interrupted or delayed for reasons beyond DDC’s control (with the exception of weather delays or “acts of god”), the obstruction or delay will be billed as an extra at the following rates:

  - “Stand down” Rate: Crew and equipment will be billed per DDC’s Standard Labor and Equipment Rate Sheet, attached, on the first day of interruption. (note if the reason for the interruption is not resolved by the end of the first day, the crew will be re-assigned and will not return until the morning of the day following the resolution date at the earliest and an additional mobilization charge may be due)

  - “Stand-by” Rate: $3,500 per day for equipment only for each additional day of interruption following the first day of interruption.

- DAMAGE TO PROPERTY: DDC will not be responsible for any damage to landscape or hardscape, including but not limited to, asphalt streets or driveways, walkways, sidewalks, curbs, etc. or existing structures. However, damage due to the negligence of DDC personnel or equipment shall be the responsibility of DDC.

- SPOILS AND TRASH REMOVAL: Others to remove and dispose of drilling/grout spoils from the working area on a continuous basis so as not to obstruct or delay the drilling operation.  This includes trash and grout/concrete generated while performing our scope of work.

- PROPER SHORING: All cuts in excess of 5 ft must be shored per Cal OSHA requirements and specifications.

- RETENTION: No retention is to be withheld. However, if DDC agrees to retention (in writing), said retention shall be released within 30 days from the successful completion of soil nail installation and testing.

- CONSTRUCTION SCHEDULE: Any construction schedule affecting the soil nail installation must be mutually agreed upon in writing.

- SUBCONTRACTS: DDC may subcontract portions of this work to properly licensed and qualified subcontractors.

- SURVEY REQUIREMENTS: DDC requires survey (provided by others) to provide and mark the perimeter of the intended Tecco Net location. If survey is required for soil nail layout, others to provide surveyor for layout. If layout is based on max spacing and does not require survey, Dakota Drilling will layout soil nail locations. Soil nail layout to be confirmed by engineer prior to drilling and installation.

- INSURANCE: DDC shall maintain in place throughout the performance of its work hereunder: (1) Worker’s Compensation coverage as required by law, (2) Automobile, and (3) Commercial general liability insurance (except condominium projects) for bodily injury and property damage coverage with a single occurrence limit of $1 million and general aggregate of $2 million. DDC will also maintain a $1 million excess liability policy. On condominium projects, Owner shall provide DDC with an OCIP at no cost whatsoever to DDC. The deductible on the OCIP shall be no greater than the deductible on DDC’s existing General Liability policy. Any excess deductible shall be at Owner’s sole expense. A waiver of subrogation is not included but can be furnished at an additional cost.

- INDEMNITY: If the Owner requires DDC to sign a contract which contains an indemnity provision, DDC shall only indemnify Owner with respect to any claim that arises directly from DDC’s active sole negligence or intentional misconduct in performing its work hereunder, and the extent of such indemnity shall be limited to DDC’s portion of the total fault causing the loss or damage on which the claim is based. DDC shall have no other responsibility to defend or pay for the Owner or its agents with respect to claims arising from or related to DDC’s work hereunder.

- PROJECT DELAYS: DDC shall be excused for delays in the completion of the contract caused by acts of God, action or non-action of Owner, Lender, inclement weather, labor disputes, acts of public utilities, public bodies, extra work, failure of Owner or General Contractor to make payments, or other contingencies unforeseen by DDC and beyond its reasonable control. In the event performance is delayed through no fault of DDC, the time for completion of DDC’s performance shall be extended by the same amount of time as the length of the delay. Additionally, DDC shall be entitled to additional compensation to fully compensate DDC for labor, materials, profit, and overhead. In the event Owner or General Contractor fails to notify DDC of a delay within 24 hours of DDC’s appointed time to perform, DDC shall be entitled to be compensated at the Delay Rates outlined in item 9 above.

- OBSTRUCTIONS: The chipping or removal of obstructions such as but not limited to concrete, shotcrete, existing earth anchors, timber, wire, rebar, steel, masonry, pipelines, etc. which interfere with the soil nail installation or testing is not included in the principal sum and costs for removal and delays will be billed as extra work on a time and materials basis at the rates shown on Dakota Drilling’s STANDARD LABOR AND EQUIPMENT RATES, attached. DDC will work with the engineer to adjust drilling angles if obstructions are encountered.

- UNFORESEEN CONDITIONS: This Contract is based upon visually observed conditions and any professional reports provided by Owner.  As a result of the nature of the services to be provided by DDC hereunder, it is possible that unforeseen conditions will arise that could not be determined by visual inspection or the provided reports prior to starting work.  In the event this occurs, additional work shall be performed on either a time and materials (see Dakota Drilling’s STANDARD LABOR AND EQUIPMENT RATES, attached) or fixed fee basis, after Owner /Contractor has been notified that such additional work is necessary and has verbally, or, if possible, in writing, approved said additional work.

- PLANS & SOILS REPORT: DDC has relied upon the plans and geotechnical reports provided to us (which are noted on page 1) for bidding purposes. DDC shall be entitled to compensation for additional work and costs incurred as a result of erroneous plans, specifications or un-anticipated site or subsurface conditions. Should conditions be encountered in the performance of DDC’s work which differ from (A) Those indicated by the contract documents or soils data furnished to DDC, or (B) Those ordinarily encountered and generally recognized as inherent in work of the character provided in the contract, an equitable adjustment will be made to cover the resulting costs. If drilled shafts are designed deeper than the soil borings, we have assumed that the material to be encountered will be similar to that which was encountered to the depth explored. Should this not be the case, any added expense is to be paid for as extra work.

- MOBILIZATIONS:  Unless noted to the contrary in the scope of work on the first page, only one (1) mobilization is included for installation of soil nails. Additional mobilizations required, for reasons not under DDC control, shall be an additional cost. Such additional mobilizations for installation will be calculated at actual cost plus 25% markup with a minimum of $5,000 each. Additional mobilizations will be an increase in the contract amount and billed as an extra.

- BACKCHARGES: No charges of any kind are to be charged to DDC’s account unless they are agreed to, and signed for, by a properly authorized representative of DDC.

- LATE CHARGES: Payment shall be made timely as previously outlined in the “Payment Schedule”. Should payment not be made timely, overdue payments will be charged interest at the lesser of 18% per annum or the maximum allowed by law.

- COLLECTION COSTS: If payment is not made as provided herein and DDC is compelled to incur any collection costs including, but not limited to, attorney’s fees and related costs, expert fees to collect all or any part of the contract price, or extras incurred during the course of the work, said fees and costs shall become collectible as an addition to the contract price.

- PAYMENT DELAYS: Should any payment due DDC, including payment for extra work, not be made when due, DDC shall have the right to stop work and to refrain from continuing work on the project until all due payments are received. Any such interruption will be a delay beyond DDC’s control and will be billed at the “Stand-by” rate. If payment is still not made within ten (10) days after its respective due date, DDC may abandon the work and pursue all rights and remedies available to it, including but not limited to, suing Owner or General Contractor for the reasonable value of work theretofore performed, and/or for breach of contract, including DDC’s lost profits, lost opportunities and overhead as well as interest and attorney’s fees thereon. DDC shall not be responsible for any additional consequential or incidental costs or time incurred by Owner or General Contractor to complete the project as a result thereof.

- LIQUIDATED DAMAGES: Unless DDC has approved a mutually agreeable schedule in writing, DDC shall not be responsible for, and is hereby released from, any and all liability for liquidated damages or other time related charges which may be assessed under the prime contract or otherwise.

- THESE TERMS PART OF ANY CONTRACT: This contract shall be made part of any contract covering this work. If Owner signs this contract, or otherwise indicates its consent, such as verbally requesting us to order materials or commence work, then this contract shall represent the entire agreement of the parties regarding performance of the work. If Owner subsequently requires DDC to sign Owner’s contract, this contract will be deemed to be part of that contract and will supersede any conflicting terms of that contract unless this contract or any paragraph or part hereof is specifically excluded in writing by the parties.

- DAKOTA DRILLING TERMS & CONDITIONS: This contract offers to the Owner the terms and conditions upon which DDC will perform the work. It may be changed, or withdrawn, by DDC at any time prior to acceptance by written notice from the Owner and will be deemed to be withdrawn if not accepted in writing within 14 days from the date appearing on the face hereof.

ACCEPTANCE

DDC is hereby authorized to furnish all materials and labor required to complete the work mentioned in this Proposal, for which I/we agree to pay the contract price mentioned in this Proposal, and according to the terms thereof. I/we acknowledge that before entering into this contract, I/we have read and agreed to the each of the provisions herein, and any attachments hereto which are made a part hereof.  Note – It is Owner’s obligation to comply with the terms, conditions, requirements and exclusions hereinabove. To the extent the Owner, General Contractor or another party’s agreement, approval, action or consent is required, it is Owner’s sole obligation to obtain such agreement, approval, action or consent, it being expressly agreed that DDC has no direct contractual relationship with said parties and is not required to seek or obtain such agreement, approval, action or consent.”

Respectfully Submitted.

DAKOTA DRILLING:	OWNER:________________________________

Signature:_________________________________	Signature:____________________________________

Print Name:________________________________	Print Name: ___________________________________

Title:  _____________________________________	Title:   ________________________________________

Dated: __________________	Dated: __________________

Notice:	Under the Mechanics Lien Law (California Civil Code) any contractor, sub-contractor, laborer, supplier or other person who helps to improve your property but is not paid for his work or supplies, has a right to enforce a claim against your property. This means that, after a court hearing, your property could be sold by a court officer and the proceeds of the sale used to satisfy the indebtedness. This can happen even if you have paid your own contractor in full, if the subcontractor, laborer, or supplier remains unpaid.

Contractors are required by law to be licensed and regulated by Contractors State License Board. Any questions concerning a Contractor should be referred to the Registrar, Contractors State Licensing Board.

Exhibit A – STANDARD LABOR & EQUIPMENT RATES

Standard

LABOR* (6 hr min.)		Hourly	Overtime

Project Manager		$135	$203

Superintendent w/ Support Vehicle		$130	$173

Foreman w/ Support Vehicle		$120	$162

Drill Operator w/ Support Vehicle		$115	$155

Grout Plant Operator w/ Support Vehicle		$110	$150

Equipment Operator		$  95	$143

Laborer		$  80	$120

EQUIPMENT** (6 hr min – Includes fuel, Excludes Operator)		Hourly	Daily

Drill – DB102		$305	$2,135

Excavator Mounted TEI Drill		$305	$2,135

Limited Access Mini Drill – Klemm 702-1		$320	$2,240

Limited Access Pile Drill – Mait Baby Drill		$395	$2,800

Foundation Pile Drill – 60 ft Depth		$420	$3,000

Portable Word / TEI Drill		min day	$1,276
	Limited Access Marini Rock Drill		min day	$1,210

Compressor – 1040 CFM – 350 psi		$275	$1,900

Compressor –   900 CFM – 350 psi 		$250	$1,750

Compressor -    350 CFM – 150 psi		$100	$   560

Compressor -    185 CFM – 125 psi		$  60	$   330

Grout Plant – CG500		min day	$   385

Grout Plant – CG680		min day	$   615

Reach Lift – 6,000 lb		$  70	$   490

Reach Lift – 10,000 lb		$  90	$   630

Skid Steer – Tracked		$  70	$   490

Mini – Excavator		$  60	$   420

Mule		min day	$   150

Support Vehicle – Ram 4500		min day	$   110

Support Vehicle – Ram 3500			min day	$     95

Support Vehicle – Ram 2500		min day	$     90

Support Vehicle – Ram 1500		min day	$     85

Generator – 3600 Watts		min day	$     95

Cement Silo		min day	$   100

Anchor Stressing Jack		min day	$   160

Anchor Turn-Table / Lazy Susan		min day	$     85

Arc Welder – 300-amp		min day	$   100

Oxygen Acetylene Torches		min day	$   110

Chain Saw		min day	$     85

Jack Hammer 90 lb		min day 	$     75

Jack Hammer 40 lb		min day	$     60

MATERIALS

Materials will be at cost + delivery + 25% mark-up

Labor and equipment will be charged per the above schedule plus 25% mark-up.	
* Note: Premium time labor rates will be provided upon request

** Note: Equivalent equipment from alternate manufacturers may be substituted

*** Note: Rental equipment will be charged at cost plus 25% mark-up

DAKOTA  DRILLING

PLEASE FILL-IN COMPLETELY AND RETURN TO DAKOTA DRILLING

By facsimile to (805) 483-5959 or Email to RHarrington@dakotadrilling.us

Property Address:

Monthly Billing Due Date: Billing to be submitted by the ______ day of the month.

CONSTRUCTION LENDER or BONDING COMPANY (if any):

NAME: _____________________________________________________________________________

STREET:___________________________________________________________________________

CITY-STATE-ZIP: ____________________________________________________________________

PHONE: ________________________ CONTACT: __________________________________________

OWNER:

NAME: _____________________________________________________________________________

STREET:___________________________________________________________________________

CITY-STATE-ZIP: ____________________________________________________________________

PHONE: ________________________ CONTACT: __________________________________________

DIRECT CONTRACTOR:

NAME: _____________________________________________________________________________

STREET:____________________________________________________________________________

CITY-STATE-ZIP: _____________________________________________________________________

PHONE: ________________________ CONTACT: __________________________________________

LICENSE #. ______________

SUB CONTRACTOR:

NAME: _____________________________________________________________________________

STREET:____________________________________________________________________________

CITY-STATE-ZIP: _____________________________________________________________________

PHONE: ________________________ CONTACT: __________________________________________

LICENSE #. ______________

PROPERTY DESCRIPTION (Please Check Applicable Boxes):

☐ Residential or ☐ Commercial

☐ New or ☐ Remodel

DAKOTA DRILLING