## PullPermit
Wood Drive Pull Permit Check List
| Description | Who | When By
1 | Open ePlanLA / LADBS permit record.
2 | Confirm status is RTI / Ready to Issue.
3 | Open the Clearance Summary Worksheet.
4 | Confirm every clearance is Approved, Approved with Conditions, Cleared, or Not Applicable.
5 | Download and save all clearance comments and conditions.
6 | Confirm all LADBS plan check disciplines are approved.
7 | Confirm soils/geology approval is complete, if applicable.
8 | Confirm contractor, license, workers’ comp, and business tax information are complete.
9 | Confirm waste hauler information, if required.
10 | Review final fee balance.
11 | Pay final fees.
12 | Download payment receipt.
13 | Issue/pull the permit.
14 | Download issued permit.
15 | Download building card/permit card.
16 | Download stamped approved plans.
17 | Download approval letters, calculations, and reports.
18 | Print or distribute approved field set.
19 | Hold preconstruction meeting.
20 | Schedule first LADBS inspection.
21 | Confirm permit, approved plans, and building card are on site.
22 | Install required site controls/BMPs.
23 | Start work.
24 | Request inspections before covering work.

## SRS Actions
SRS Actions
| Description | Who | When By
1 | Get hauler information for permit | Dave | 2026-08-14 | get info from Randy
2 | Pull permit via Eplan | Dave&Luke | 2026-08-21
3 | Meet Doug and Randy to agree: * SRS fees ($665,000 - $591,996 = $73,004 * Scope of Work * Schedule | Dave&Luke | 2026-08-21
4 | Create Project Schedule (for client) | Dave | 2026-08-28
5 | Determine what inspectors are needed | Dave
6 | Hire Civil to stake property lines (per GPI) | Dave
7 | Hire Feffer as Registered Deputy Inspectors (Soils) | Dave
8 | Hire concrete testing inspectors gor grout ? | Dave
9 | Set up Pre-Constriuction Meeting | Dave
10 | Coordinate with plumber (via owner)
11 | Neighbor notifications (after schedule laydown pla))
12 | Camera for site? - notifications?
13 | Invoicing flow
14 | Hire surveyor to layout property lines | Payan Surveying Inc |  | 951 356 6456
15 | Dig Alert

## Dakota Actions
Dakota Actions
| Description | Who | When By
1 | Provide insurance info for permit
2 | Provide Hauler info for permit
3 | Receive deposit
4 | Order materials
5
6
7
8
9
10